## FPs-Team3
Step - 1 : Unadjusted function point calcluation | [8 empty] | Comments
This sheet calculates the below items as mentioned:
Sno | Function Name | Function Type | RET | DET | FTR | Complexity | Rating |  | Step - 1 : Unadjusted function points (UFP)
1 | Create Instances | EI |  | 16+ | 1 | Average | 4 |  | Step - 2 : UFP into Size (KSLOC) |  | 3
2 | Update/Delete Instances | EI |  | 16+ | 1 | Average | 4 |  | Step - 3: Function point estimation |  | 3
3 | Create links | EI |  | 16+ | 1 | Average | 4 |  |  |  | 3
4 | Update/Delete links | EI |  | 10 | 1 | Average | 4 |  |  |  | 5
5 | Generate report | EO |  | 20 | 1 | Average | 5 |  |  |  | 0
6 | View traceability | EQ |  | 20 | 1 | Average | 5 |  |  |  | 0
7 | Models | EIF | 1 | 10 |  | Low | 5 |  |  |  | 1
8 | Links | EIF | 1 | 10 |  | Low | 5 |  |  |  | 5
9 | Property | EIF | 1 | 10 |  | Low | 5 |  |  |  | 1
10 | Project | EIF | 1 | 5 |  | Low | 5 |  |  |  | 1
11 | Instances | EIF | 1 | 10 |  | Low | 5 |  |  |  | 4
12 | User | EIF | 1 | 10 |  | Low | 5 |  |  |  | 4
13 | Roles | EIF | 1 | 5 |  | Low | 5 |  |  |  | 30
[6 empty] | UFPs | 61
| Step - 2 : UFP into Size (KSLOC) | [6 empty] | Step - 3: Function point estimation
[8 empty] | General System Characteristic |  | Brief Description
| This is actually used in the COCOMO estimate | [6 empty] | 1 | Data communications | How many communication facilities are there to aid in the transfer or exchange of information with the application or system?
[8 empty] | 2 | Distributed data processing | How are distributed data and processing functions handled?
[8 empty] | 3 | Performance | Was response time or throughput required by the user?
| Size= | UFP x 53 (Java) | [5 empty] | 4 | Heavily used configuration | How heavily used is the current hardware platform where the application will be executed?
| Size(KSLOC)= | 3.233 | [5 empty] | 5 | Transaction rate | How frequently are transactions executed daily, weekly, monthly, etc.?
| No reuse of code from other projects | [6 empty] | 6 | On-Line data entry | What percentage of the information is entered On-Line?
| No REVL | [6 empty] | 7 | End-user efficiency | Was the application designed for end-user efficiency?
| No autmatically code translator tool | [6 empty] | 8 | On-Line update | How many ILF’s are updated by On-Line transaction?
| No siziing software maintanence | [6 empty] | 9 | Complex processing | Does the application have extensive logical or mathematical processing?
[8 empty] | 10 | Reusability | Was the application developed to meet one or many user’s needs?
[8 empty] | 11 | Installation ease | How difficult is conversion and installation?
[8 empty] | 12 | Operational ease | How effective and/or automated are start-up, back-up, and recovery procedures?
[8 empty] | 13 | Multiple sites | Was the application specifically designed, developed, and supported to be installed at multiple sites for multiple organizations?
[8 empty] | 14 | Facilitate change | Was the application specifically designed, developed, and supported to facilitate change?
[9 empty] | VAF | 0.95
[9 empty] | FP | 57.95
Multiply the function points by 18 to get person hours
1043.1

## FPs-Team4
Step - 1 : Unadjusted function point calcluation | [8 empty] | Comments
This sheet calculates the below items as mentioned:
Sno | Function Name | Type | RET | DET | FTR | Complexity | Rating |  | Step - 1 : Unadjusted function points (UFP)
1 | Login | EI |  | 3 | 1 | Low | 3 |  | Step - 2 : UFP into Size (KSLOC)
2 | Create model | EI |  | 16+ | 1 | Average | 4 |  | Step - 3: Function point estimation
3 | Update Model | EI |  | 16+ | 1 | Average | 4
4 | Create Property | EI |  | 8 | 1 | Low | 3
5 | Update Property | EI |  | 8 | 1 | Low | 3
8 | Create user | EI |  | 8 | 1 | Low | 3
9 | Delete User | EI |  | 8 | 1 | Low | 3
10 | Create role | EI |  | 8 | 2 | Average | 4
11 | Update roles | EI |  | 8 | 2 | Average | 4
12 | Create Project | EI |  | 8 | 1 | Low | 3
14 | Models | ILF | 1 | 10 |  | Low | 7
15 | Links | ILF | 1 | 10 |  | Low | 7
16 | Property | ILF | 1 | 10 |  | Low | 7
17 | Project | ILF | 1 | 5 |  | Low | 7
18 | Instances | ILF | 1 | 10 |  | Low | 7
19 | User | ILF | 1 | 10 |  | Low | 7
20 | Roles | ILF | 1 | 5 |  | Low | 7
[6 empty] | UFP= | 83
| Step - 2 : UFP into Size (KSLOC) | [6 empty] | Step - 3: Function point estimation
| This is actually used in the COCOMO estimate | [6 empty] | General System Characteristic |  | Brief Description | Scale(0-5)
[8 empty] | 1 | Data communications | How many communication facilities are there to aid in the transfer or exchange of information with the application or system? | 3
[8 empty] | 2 | Distributed data processing | How are distributed data and processing functions handled? | 3
| Size= | UFP x 53 (Java) | [5 empty] | 3 | Performance | Was response time or throughput required by the user? | 4
| Size(KSLOC)= | 4.399 | [5 empty] | 4 | Heavily used configuration | How heavily used is the current hardware platform where the application will be executed? | 3
| No reuse of code from other projects | [6 empty] | 5 | Transaction rate | How frequently are transactions executed daily, weekly, monthly, etc.? | 5
| No REVL | [6 empty] | 6 | On-Line data entry | What percentage of the information is entered On-Line? | 0
| No autmatically code translator tool | [6 empty] | 7 | End-user efficiency | Was the application designed for end-user efficiency? | 4
| No siziing software maintanence | [6 empty] | 8 | On-Line update | How many ILF’s are updated by On-Line transaction? | 0
[8 empty] | 9 | Complex processing | Does the application have extensive logical or mathematical processing? | 4
[8 empty] | 10 | Reusability | Was the application developed to meet one or many user’s needs? | 4
[8 empty] | 11 | Installation ease | How difficult is conversion and installation? | 4
[8 empty] | 12 | Operational ease | How effective and/or automated are start-up, back-up, and recovery procedures? | 4
[8 empty] | 13 | Multiple sites | Was the application specifically designed, developed, and supported to be installed at multiple sites for multiple organizations? | 3
[8 empty] | 14 | Facilitate change | Was the application specifically designed, developed, and supported to facilitate change? | 4
45
[9 empty] | VAF | 1.1
[9 empty] | FP | 91.3
Multiply the function points by 18 to get person hours
1643.4

## E-scale
E-calculation | This sheet calculates the scaling factors for the COCOMO estimate
| Scale | Very Low | Low | Nominal | High | Very High | Extra High | Final values
PREC | Process | thoroughly precendented | largely precendented | somewhat precendented | generally precendented | largely familiar | throughly familiar
| Value | 6.2 | 4.96 | 3.72 | 2.48 | 1.24 | 0
| Yes(1)/No(0) | 0 | 0 | 0 | 1 | 0 | 0 | 2.48
FLEX | Schedule | rigorous | occasional relaxation | some relaxation | general conformity | some conformity | general goals
| Value | 5.07 | 4.05 | 3.04 | 2.03 | 1.01 | 0
| Yes(1)/No(0) | 0 | 0 | 0 | 1 | 0 | 0 | 2.03
RESL | Risks identified | little (20%) | some (40%) | often (60%) | generally(75 %) | Mostly(90%) | All
| Value | 7.07 | 5.65 | 4.24 | 2.83 | 1.41 | 0
| Yes(1)/No(0) | 0 | 0 | 0 | 1 | 0 | 0 | 2.83
TEAM | Stakeholder interaction | very difficult interactions | some difficult interactions | basically cooperative | largely cooperative | Highly cooperative | seamless interactions
| Value | 5.48 | 4.38 | 3.29 | 2.19 | 1.1 | 0
| Yes(1)/No(0) | 0 | 0 | 0 | 0 | 1 | 0 | 1.1
PMAT | CMMI Level | 1- lower | 1-upper | 2 | 3 | 4 | 5
| Value | 7.8 | 6.24 | 4.68 | 3.12 | 1.56 | 0
| Yes(1)/No(0) | 0 | 0 | 1 | 0 | 0 | 0 | 4.68
[6 empty] | Overall (SF) |  | 13.12
[6 empty] | E= | B+0.01xSF
[6 empty] | E= | 1.0412

## EarlyEstimate-Team4
Cost Drivers-Step 4 | [7 empty] | Comments
This sheet calculates the person hours and cost drivers for Team-4 using COCOMO early estimate model
SCALE | VERY LOW | LOW | NOMINAL | HIGH | VERY HIGH | EXTRA HIGH
VALUE | 1 | 2 | 3 | 4 | 5 | 6
PERS- Personnel Capability | [6 empty] | PM-Person Months
Factor | ACAP | PCAP | PCON | Sum | PERS Value
Desc | Analyst Ability | Programmer Capability | Personnel Turnover |  | Refer below table |  | EM-Overall Sum
Range | (1-5) | (1-5) | (1-5) | - | -
Value | 3 | 3 | 5 | 11 | 0.83 |  | PERS | RCPX | RUSE | PDIF | PREX | SCED | FCIL | Product | E-Scale | Size
[7 empty] | 0.83 | 1.33 | 0.95 | 1 | 0.87 | 1 | 0.73 | 0.66603 | 1.0412 | 4.399
[9 empty] | Person Months= | A x (Size) ^E x Sum(EM)
[9 empty] | Person Months= | 9.1559
[9 empty] | Person Hours= | 1391.7028
RCPX- Product Reliability & Complexity | [6 empty] | PDIF-Platform difficulty
Factor | RELY | DATA | CPLX | DOCU | Sum | RCPX Value | Factor | TIME | STOR | PVOL | Sum | PDIF Value
Desc | Required Software Reliability | DB size | Product Complexity | Documentation to match Lifecycle |  | Refer below table | Desc | Execution time constraint | Main Storage Constraint | Platform Volatility |  | Refer below table
Range | (1-5) | (2-5) | (1-6) | (1-5) | - | - | Range | (3-6) | (3-6) | (2-5) | - | -
Value | 4 | 3 | 3 | 3 | 13 | 1.33 | Value | 3 | 3 | 3 | 9 | 1
RUSE- Developed for Reuseability | [6 empty] | SCED-Required Development Schedule
Factor | RUSE | Value |  |  |  |  | Factor | SCED | Value
Desc | Developed for Reuseability | Refer below table |  |  |  |  | Desc | Developed for Reuseability | Refer below table
Range | (2-6) | [5 empty] | Range | (1-5)
Value | 2 | 0.95 |  |  |  |  | Value | 2 | 1
PREX-Personnel Experience | [6 empty] | FCIL-Facilities
Factor | APEX | PLEX | LTEX | Sum | Value |  | Factor | TOOL | SITE | Sum | Value
Desc | Application Experience | Platform experience | Language & tool experience |  | Refer below table |  | Desc | Use of software tools | Multisite development |  | Refer below table
Range | (1-5) | (1-5) | (1-5) | - | - |  | Range | (1-5) | (1-6) | - | -
Value | 3 | 4 | 3 | 10 | 0.87 |  | Value | 4 | 5 | 9 | 0.73

## EarlyEstimate-Team3
Cost Drivers-Step 4 | [8 empty] | Comments
This sheet calculates the person hours for Team-3 and cost drivers using COCOMO early estimate model
SCALE | VERY LOW | LOW | NOMINAL | HIGH | VERY HIGH | EXTRA HIGH
VALUE | 1 | 2 | 3 | 4 | 5 | 6
PERS- Personnel Capability | [6 empty] | PM-Person Months
Factor | ACAP | PCAP | PCON | Sum | PERS Value
Desc | Analyst Ability | Programmer Capability | Personnel Turnover |  | Refer below table
Range | (1-5) | (1-5) | (1-5) | - | - |  | EM-Overall Sum
Value | 3 | 3 | 5 | 11 | 0.83
[7 empty] | PERS | RCPX | RUSE | PDIF | PREX | SCED | FCIL | Product | E-Scale | Size
[7 empty] | 0.83 | 1 | 0.95 | 1 | 1.33 | 1 | 0.73 | 0.76555 | 1.0412 | 3.233
[9 empty] | Person Months= | A x (Size) ^E x Sum(EM)
[9 empty] | Person Months= | 7.637
[9 empty] | Person Hours= | 1160.8299
RCPX- Product Reliability & Complexity | [6 empty] | PDIF-Platform difficulty
Factor | RELY | DATA | CPLX | DOCU | Sum | RCPX Value | Factor | TIME | STOR | PVOL | Sum | PDIF Value
Desc | Required Software Reliability | DB size | Product Complexity | Documentation to match Lifecycle |  | Refer below table | Desc | Execution time constraint | Main Storage Constraint | Platform Volatility |  | Refer below table
Range | (1-5) | (2-5) | (1-6) | (1-5) | - | - | Range | (3-6) | (3-6) | (2-5) | - | -
Value | 4 | 2 | 3 | 3 | 12 | 1 | Value | 3 | 3 | 3 | 9 | 1
RUSE- Developed for Reuseability | [6 empty] | SCED-Required Development Schedule
Factor | RUSE | Value |  |  |  |  | Factor | SCED | Value
Desc | Developed for Reuseability | Refer below table |  |  |  |  | Desc | Developed for Reuseability | Refer below table
Range | (2-6) | [5 empty] | Range | (1-5)
Value | 2 | 0.95 |  |  |  |  | Value | 2 | 1
PREX-Personnel Experience | [6 empty] | FCIL-Facilities
Factor | APEX | PLEX | LTEX | Sum | Value |  | Factor | TOOL | SITE | Sum | Value
Desc | Application Experience | Platform experience | Language & tool experience |  | Refer below table |  | Desc | Use of software tools | Multisite development |  | Refer below table
Range | (1-5) | (1-5) | (1-5) | - | - |  | Range | (1-5) | (1-6) | - | -
Value | 2 | 2 | 2 | 6 | 1.33 |  | Value | 3 | 4 | 7 | 0.73

## Estimate&Schedule
Comments | This sheet computes the overall effort and the schedule.
Estimated Effort
| Size | SCED | E-scale | PM-Basic | PM-teamwise | PM | Schedule for Dev & Arch
Team-3 | 3.233 | N/A | N/A | N/A | 10.3352 | 7.9121
Team-4 | 4.399 | N/A | N/A | N/A | 14.0626 | 9.3662
Overall | 7.632 | 1 | 1.0412 | 24.3978 |  | 17.2783 | 8.7829
[5 empty] | Person Hours | 2626.3011 | 1335.0021
[5 empty] | Weeks | 31.2655 | 15.8929
Available effort
Practicum End Date | Practicum Start Date | Number of Weeks | Number of Hrs | Team-3 | Team-4
2017-04-15 | 2016-08-23 | 33.5714 | 2820 | 1208.5714 | 1611.4286