## UUCW
Figure 1: Use case Diagram
|  |  |  | Use Case | Use Case Classification
|  |  |  | Manage Model | Complex
|  |  |  | Manage Users | Complex
|  |  |  | Manage Links | Complex
|  |  |  | Manage Instances | Complex
|  |  |  | View Traceability | Complex
Unadjusted Use Case Weight (UUCW)
Use Case Classification | No. of Transactions | Weight | UseCases
Simple | 1 to 3 transactions | 5 | 0
Average | 4 to 7 transactions | 10 | 0
Complex | 8 or more transactions | 15 | 5
UUCW = (Total No. of Simple Use Cases x 5) + (Total No. Average Use Case x 10) + (Total No. Complex Use Cases x 15) |  |  | 75

## UAW
Unadjusted Actor Weight (UAW)
Actor Classification | Type of Actor | Weight | Weight
Simple | External system that must interact with the system using a well-defined API | 1 | 0
Average | External system that must interact with the system using standard communication protocols (e.g. TCP/IP, FTP, HTTP, database) | 2 | 0
Complex | Human actor using a GUI application interface | 3 | 2
UAW = (Total No. of Simple actors x 1) + (Total No. Average actors x 2) + (Total No. Complex actor x 3) |  |  | 6

## TCF
Technical Complexity Factor (TCF)
Factor | Description | Weight | Factor | Weight x Factor
T1 | Distributed system | 2 | 0 | 0
T2 | Response time/performance objectives | 1 | 4 | 4
T3 | End-user efficiency | 1 | 4 | 4
T4 | Internal processing complexity | 1 | 5 | 5
T5 | Code reusability | 1 | 5 | 5
T6 | Easy to install | 0.5 | 4 | 2
T7 | Easy to use | 0.5 | 4 | 2
T8 | Portability to other platforms | 2 | 2 | 4
T9 | System maintenance | 1 | 3 | 3
T10 | Concurrent/parallel processing | 1 | 4 | 4
T11 | Security features | 1 | 5 | 5
T12 | Access for third parties | 1 | 0 | 0
T13 | End user training | 1 | 4 | 4
TF (Sum) = |  |  |  | 42
TCF= | 0.6 + (TF/100)
TCF= | 1.02

## ECF
Environmental Complexity Factor (ECF)
Factor | Description | Weight | Factor | Weight x Factor
E1 | Familiarity with development process used | 1.5 | 2 | 3
E2 | Application experience | 0.5 | 2 | 1
E3 | Object-oriented experience of team | 1 | 4 | 4
E4 | Lead analyst capability | 0.5 | 2 | 1
E5 | Motivation of the team | 1 | 5 | 5
E6 | Stability of requirements | 2 | 4 | 8
E7 | Part-time staff | -1 | 0 | 0
E8 | Difficult programming language | -1 | 1 | -1
| EF (Sum) = |  |  | 21
ECF= | 1.4 + (-0.03 x EF)
ECF= | 0.77

## Estimated Effort
Use Case Points (UCP)
UCP = (UUCW + UAW) x TCF x ECF
UCP = | 63.6174
Estimated Effort = UCP x Hours/UCP
Estimated Effort = | 1781.2872
(Hours/UCP may range from 20 to 28 - Scheider and Winters’ range and we are considering the highest range since this is the 1st time we are using this approach)
Total Number of weeks= | 21.2058

## Availabe Effort
Practicum End Date | Practicum Start Date | Number of Weeks | Number of Hrs | Team-3 | Team-4
2017-04-15 | 2016-08-23 | 33.5714 | 2820 | 1208.5714 | 1611.4286